## الورقة1
Defect # | Status | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
BUG_001 | Closed | Sara Abdulwahab | V2 | ADD_FIL_03 | User is logged in as an admin and is on the Filters page. "1- Click on the add icon on the top of the Filters page 2- Enter a valid Sort order in the Sort order field 3- submit the form" | The System will accept the Sort order and will not show any errors to it beside showing errors related to other unfilled fields not related to this test case | system does not accept the field and show invalid input
BUG_002 | Closed | Sara Abdulwahab | V2 | ADD_FIL_04 | User is logged in as an admin and is on the Filters page. "1- Click on the add icon on the top of the Filters page 2- Enter a invalid Sort order in the Sort order field 3- submit the form" | The System will not accept the Sort order and will show an error indicating invalid entered Sort order beside showing errors related to other unfilled fields not related to this test case | system accepts the input.
BUG_003 | Closed | Sara Abdulwahab | V2 | ADD_FIL_07 | User is logged in as an admin and is on the Filters page. "1- Click on the add icon on the top of the Filters page 2- Enter a invalid FilterValue Name 3- submit the form" | The System will not accept the FilterValue Name and will show an error indicating invalid entered FilterValue Name beside showing errors related to other unfilled fields not related to this test case | system accepts the FilterValue name
BUG_004 | Closed | Sara Abdulwahab | V2 | ADD_FIL_08 | User is logged in as an admin and is on the Filters page. "1- Click on the plus icon on the top of the Filters page 2- Leave the FilterValue Name blank 3- submit the form" | The system show an error indicating that this field is required beside showing errors related to the other unfilled fields (not related to this case) | system accepts the field
BUG_005 | Closed | Sara Abdulwahab | V2 | ADD_FIL_11 | User is logged in as an admin and is on the Filters page. 1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Leave optional fields empty 4. Submit the form | The item is not added | The item is added successfully
BUG_006 | Closed | Sara Abdulwahab | V2 | ADD_FIL_12 | User is logged in as an admin and is on the Filters page. 1. Click the Plus button on the top of the page 2. Enter invalid data (e.g., letters in a numeric field) 3. Submit the form | No error displayed | An error message is displayed, and submission should not proceed
BUG_007 | Closed | Sara Abdulwahab | V2 | ADD_FIL_16 | User is logged in as an admin and is on the Filters page. 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | item is not added | item is added and the confirmation message appear
BUG_008 | Closed | Sara Abdulwahab | V2 | ADD_FIL_17 | User is logged in as an admin and is on the Filters page. 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | item is not added | The form reset to empty fields after submission
BUG_009 | Closed | Sara Abdulwahab | V2 | DEL_FIL_03 | User is logged in as an admin and is on the Filters page. 1. Open Filters page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Filters page." | All the selected items are removed from the UI after confirmation. | The selected items are not removed from the UI
BUG_010 | Closed | Sara Abdulwahab | V2 | DEL_FIL_04 | User is logged in as an admin and is on the Filters page. 1. Open Filters page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system." | Items is permanently removed from the database and do not reappear after refresh | Items are not removed from the database
BUG_011 | Closed | Sara Abdulwahab | V2 | DEL_FIL_08 | User is logged in as an admin and is on the Filters page. "1. Open Filters page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response." | A "Deletion successful" message appears after removing items. | The item is not deleted
BUG_012 | Closed | Sara Abdulwahab | V2 | ADD_OPT_03 | User is logged in as an admin and is on the Optionspage. 1- Click on the plus icon on the top of the Optionspage 2- Leave theOption name blank 3- submit the form" | The system show an error indicating that this field is required beside showing errors related to the other unfilled fields (not related to this case) | system does not show an error
BUG_013 | Closed | Sara Abdulwahab | V2 | ADD_OPT_04 | User is logged in as an admin and is on the Options page. "1- Click on the add icon on the top of the page 2- Check that the Options Type list contains all requited options 3- Submit the form" | The system displays all the available valid option types in the Options Type list | system does not display all the valid options
BUG_014 | Closed | Sara Abdulwahab | V2 | ADD_OPT_08 | User is logged in as an admin and is on the Options page. 1- Click on the add icon on the top of the Options page 2- Enter a valid Sort order in the Sort order field 3- submit the form" | The System will accept the Sort order and will not show any errors to it beside showing errors related to other unfilled fields not related to this test case | system does not accept the field and show invalid input
BUG_015 | Closed | Sara Abdulwahab | V2 | ADD_OPT_09 | User is logged in as an admin and is on the Options page. 1- Click on the add icon on the top of the Options page 2- Enter a invalid Sort order in the Sort order field 3- submit the form" | The System will not accept the Sort order and will show an error indicating invalid entered Sort order beside showing errors related to other unfilled fields not related to this test case | system accepts the input
BUG_016 | Closed | Sara Abdulwahab | V2 | ADD_OPT_12 | User is logged in as an admin and is on the Options page. 1- Click on the add icon on the top of the Options page 2- Enter a invalid Option Value Name 3- submit the form" | The System will not accept the Option Value Name and will show an error indicating invalid entered Option Value Name beside showing errors related to other unfilled fields not related to this test case | system accepts the option Value name
BUG_017 | Closed | Sara Abdulwahab | V2 | ADD_OPT_13 | User is logged in as an admin and is on the Options page. " 1- Click on the plus icon on the top of the Options page 2- Leave the Option Value Name blank 3- submit the form" | The system show an error indicating that this field is required beside showing errors related to the other unfilled fields (not related to this case) | system accepts the field
BUG_018 | Closed | Sara Abdulwahab | V2 | ADD_OPT_16 | User is logged in as an admin and is on the Options page. 1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Leave optional fields empty 4. Submit the form | The item should be added successfully | The item is not added
BUG_019 | Closed | Sara Abdulwahab | V2 | ADD_OPT_17 | User is logged in as an admin and is on the Options page. 1. Click the Plus button on the top of the page 2. Enter invalid data (e.g., letters in a numeric field) 3. Submit the form | An error message should be displayed, and submission should not proceed | No error displayed
BUG_020 | Closed | Sara Abdulwahab | V2 | ADD_OPT_21 | User is logged in as an admin and is on the Options page. 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | A success message should appear, confirming the addition | item is not added
BUG_021 | Closed | Sara Abdulwahab | V2 | ADD_OPT_22 | User is logged in as an admin and is on the Options page. 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | The form should reset to empty fields after submission | item is not added
BUG_022 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_03 | User is logged in as an admin and is on the Optionspage. 1- Click on the Edit icon 2- Leave theOption name blank 3- submit the form" | The system show an error indicating that this field is required | system does not show an error
BUG_023 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_04 | User is logged in as an admin and is on the Options page. 1- Click on the Edit icon 2- Check that the Options Type list contains all requited options 3- Submit the form" | The system displays all the available valid option types in the Options Type list | system does not display all the valid options
BUG_024 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_08 | User is logged in as an admin and is on the Options page. 1- Click on the Edit icon 2- Enter a valid Sort order in the Sort order field 3- submit the form" | The System will accept the Sort order and will not show any errors to it | system does not accept the field and show invalid input
BUG_025 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_09 | User is logged in as an admin and is on the Options page. 1- Click on the Edit icon 2- Enter a invalid Sort order in the Sort order field 3- submit the form" | The System will not accept the Sort order and will show an error indicating invalid entered Sort order | system accepts the input
BUG_026 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_12 | User is logged in as an admin and is on the Options page. 1- Click on the Edit icon 2- Enter a invalid Option Value Name 3- submit the form" | The System will not accept the Option Name and will show an error indicating invalid entered Option Value Name | system accepts the option Value name
BUG_027 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_13 | User is logged in as an admin and is on the Options page. 1- Click on the Edit icon 2- Leave the Option Value Name blank 3- submit the form" | The system show an error indicating that this field is required | system accepts the field
BUG_028 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_16 | User is logged in as an admin and is on the Options page. 1. Click the ""Edit"" button beside an existing Options items. 2. Modify a field with invalid data (e.g., incorrect format). 3. Click ""Save"" button" | System displays an error message and does not save changes | system sace changes without errors
BUG_029 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_17 | User is logged in as an admin and is on the Options page. 1. Click the ""Edit"" button beside an existing Options items. 2. Modify any field. 3. Click ""Cancel"" or navigate away." | Changes are discarded, and the original data remains unchanged | system does not discard changes
BUG_030 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_21 | User is logged in as an admin and is on the Options page. 1. Click the ""Edit"" button beside an existing Options items. 2. Modify any field. 3. Click outside the form without saving." | Changes are not saved, and the original data remains | changes saved
BUG_031 | Closed | Sara Abdulwahab | V2 | EDIT_OPT_22 | User is logged in as an admin and is on the Options page. 1. Click the ""Edit"" button beside an existing Options items 2. Click the ""Back"" button" | System navigates back to the item list page without saving any changes | System navigates back to the item list page without saving any changes
BUG_032 | Closed | Sara Abdulwahab | V2 | DEL_OPT_03 | User is logged in as an admin and is on the Options page. 1. Open Options page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Options page." | All the selected items are removed from the UI after confirmation. | The selected items are not removed from the UI
BUG_033 | Closed | Sara Abdulwahab | V2 | DEL_OPT_04 | User is logged in as an admin and is on the Options page. 1. Open Options page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system." | Items is permanently removed from the database and do not reappear after refresh | Items are not removed from the database
BUG_034 | Closed | Sara Abdulwahab | V2 | DEL_OPT_08 | User is logged in as an admin and is on the Options page. 1. Open Options page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response." | A "Deletion successful" message appears after removing items. | The item is not deleted
BUG_035 | Closed | Sara Abdulwahab | V2 | ADD_REV_14 | User is logged in as an admin and is on the Reviews page. 1. Click the Plus button on the top of the page 2. Leave required fields empty 3. Submit the form | The system should display an error message and prevent submission | system does not display the error
BUG_036 | Closed | Sara Abdulwahab | V2 | ADD_REV_15 | User is logged in as an admin and is on the Reviews page. 1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Leave optional fields empty 4. Submit the form | The item should be added successfully
BUG_037 | Closed | Sara Abdulwahab | V2 | ADD_REV_19 | User is logged in as an admin and is on the Reviews page. 1. Click the Plus button on the top of the page 2. Leave required fields empty | The "Submit" button should remain disabled | submit button is not disabled
BUG_038 | Closed | Sara Abdulwahab | V2 | ADD_REV_20 | User is logged in as an admin and is on the Reviews page. 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | A success message should appear, confirming the addition | item not added
BUG_039 | Closed | Sara Abdulwahab | V2 | EDIT_REV_13 | User is logged in as an admin and is on the Reviews page. "1. Click the ""Edit"" button beside an existing Reviews items. 2. Modify a field with invalid data (e.g., incorrect format). 3. Click ""Save"" button" | System displays an error message and does not save changes | item can not be edited
BUG_040 | Closed | Sara Abdulwahab | V2 | EDIT_REV_15 | User is logged in as an admin and is on the Reviews page. "1. Click the ""Edit"" button beside an existing Reviews items. 2. Do not modify any field. 3. Check if the ""Save"" or ""Update"" button is active." | "Save" button remains disabled | "Save" button remains enabled
BUG_041 | Closed | Sara Abdulwahab | V2 | EDIT_REV_16 | User is logged in as an admin and is on the Reviews page. "1. Click the ""Edit"" button beside an existing Reviews items. 2. Navigate back to the submissions list." | Updated data appears in the list | item can not be edited
BUG_042 | Closed | Sara Abdulwahab | V2 | DEL_REV_03 | User is logged in as an admin and is on the Reviews page. "1. Open Reviews page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Reviews page." | All the selected items are removed from the UI after confirmation. | The selected items are not removed from the UI
BUG_043 | Closed | Sara Abdulwahab | V2 | DEL_REV_04 | User is logged in as an admin and is on the Reviews page. "1. Open Reviews page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system." | Items is permanently removed from the database and do not reappear after refresh | Items are not removed from the database
BUG_044 | Closed | Sara Abdulwahab | V2 | DEL_REV_08 | User is logged in as an admin and is on the Reviews page. "1. Open Reviews page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response." | A "Deletion successful" message appears after removing items. | The item is not deleted
BUG_045 | Closed | Khaled Wael | V2 | ADD_CG_12 | User is logged in as an admin and is on the Custom Groups page. "1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Enter valid data in optional fields 4. Submit the form" | The item is added successfully, and a confirmation message should appear | The item is not added successfully, and a confirmation message should appear
BUG_046 | Closed | Khaled Wael | V2 | ADD_CG_14 | User is logged in as an admin and is on the Custom Groups page. "1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Leave optional fields empty 4. Submit the form" | The item is added successfully | The item is not added successfully, and a confirmation message should appear
BUG_047 | Closed | Khaled Wael | V2 | ADD_CG_16 | User is logged in as an admin and is on the Custom Groups page. "1. Click the Plus button on the top of the page 2. Enter the same data as an existing item 3. Submit the form" | The system display an error and prevent duplication | The item is not added successfully, and a confirmation message should appear
BUG_048 | Closed | Khaled Wael | V2 | ADD_CG_19 | User is logged in as an admin and is on the Custom Groups page. "1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form" | A success message appear, confirming the addition | The item is not added successfully, and a confirmation message should appear
BUG_049 | Closed | Khaled Wael | V2 | ADD_CG_20 | User is logged in as an admin and is on the Custom Groups page. "1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form" | The form reset to empty fields after submission | The item is not added successfully, and a confirmation message should appear
BUG_050 | Closed | Khaled Wael | V2 | ADD_CG_21 | User is logged in as an admin and is on the Custom Groups page. "1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form" | The user is redirected to the item list page | The item is not added successfully, and a confirmation message should appear
BUG_051 | Closed | Khaled Wael | V2 | EDIT_CG_12 | User is logged in as an admin and is on the Custom groups page. "1. Click the ""Edit"" button beside an existing Custom groups items. 2. Modify the required fields with valid data. 3. Click ""Save"" " | Submission updates successfully with a confirmation message | item can not be edited
BUG_052 | Closed | Khaled Wael | V2 | EDIT_CG_13 | User is logged in as an admin and is on the Custom groups page. "1. Click the ""Edit"" button beside an existing Custom groups items. 2. Modify a field with invalid data (e.g., incorrect format). 3. Click ""Save"" button" | System displays an error message and does not save changes | item can not be edited
BUG_053 | Closed | Khaled Wael | V2 | EDIT_CG_15 | User is logged in as an admin and is on the Custom groups page. "1. Click the ""Edit"" button beside an existing Custom groups items. 2. Do not modify any field. 3. Check if the ""Save"" or ""Update"" button is active." | "Save" button remains disabled | "Save" button remains enabled
BUG_054 | Closed | Khaled Wael | V2 | EDIT_CG_16 | User is logged in as an admin and is on the Custom groups page. "1. Click the ""Edit"" button beside an existing Custom groups items. 2. Navigate back to the submissions list." | Updated data appears in the list | item can not be edited
BUG_055 | Closed | Khaled Wael | V2 | DEL_CG_03 | User is logged in as an admin and is on the Custom Groups page. "1. Open Custom Groups page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Custom Groups page." | All the selected items are removed from the UI after confirmation. | The selected items are not removed from the UI
BUG_056 | Closed | Khaled Wael | V2 | DEL_CG_04 | User is logged in as an admin and is on the Custom Groups page. "1. Open Custom Groups page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system." | Items is permanently removed from the database and do not reappear after refresh | Items are not removed from the database
BUG_057 | Closed | Khaled Wael | V2 | DEL_CG_08 | User is logged in as an admin and is on the Custom Groups page. "1. Open Custom Groups page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response." | A "Deletion successful" message appears after removing items. | The item is not deleted
BUG_058 | Closed | Khaled Wael | V2 | ADD_CF_16 | User is on the "Add New Item" page. "1. Fill all required fields with valid data. 2. Click ""Submit""." | The item should be added successfully, and a success message should appear. | The item is not added successfully, and a confirmation message should appear
BUG_059 | Closed | Khaled Wael | V2 | ADD_CF_18 | User is on the "Add New Item" page. "1. Fill only the required fields. 2. Leave optional fields blank. 3. Click ""Submit""." | The item should be added successfully. | The item is not added successfully, and a confirmation message should appear
BUG_060 | Closed | Khaled Wael | V2 | ADD_CF_20 | An item with the same name already exists. "1. Enter details of an existing item. 2. Click ""Submit""." | The system should display a "Duplicate entry" error. | The item is not added successfully, and a confirmation message should appear
BUG_061 | Closed | Khaled Wael | V2 | ADD_CF_23 | User is on the "Add New Item" page. "1. Fill all required fields. 2. Click ""Submit""." | A success message should appear. | The item is not added successfully, and a confirmation message should appear
BUG_062 | Closed | Khaled Wael | V2 | ADD_CF_24 | User successfully adds an item. 1. Observe the form after submission. | The form should reset to blank fields. | The item is not added successfully, and a confirmation message should appear
BUG_063 | Closed | Khaled Wael | V2 | ADD_CF_25 | User successfully adds an item. "1. Click ""Submit""." | The system should redirect to the item list page. | The item is not added successfully, and a confirmation message should appear
BUG_064 | Closed | Khaled Wael | V2 | Edit_CF_01 | User is on the "Edit Custom Field" page with a pre-filled name. "Click on the ""Custom Field Name"" field. Clear the existing text. Enter a valid name (e.g., ""Updated Field 1""). Click ""Save"". Refresh the page." | The name should be saved and displayed after refresh. | The name is not saved; it reverts to the old value.
BUG_065 | Closed | Khaled Wael | V2 | Edit_CF_02 | User is on the "Edit Custom Field" page. "Click on the ""Custom Field Name"" field. Clear the existing text. Enter an invalid name (e.g., ""@@!!""). Click ""Save"". Refresh the page." | The system should show an error and prevent saving. | The name is not saved, but no error is displayed.
BUG_066 | Closed | Khaled Wael | V2 | Edit_CF_03 | User is on the "Edit Custom Field" page. "Click on the ""Custom Field Name"" field. Clear the text completely. Click ""Save"". Refresh the page." | The system should show an error and prevent saving. | The name is not saved, but no error is displayed.
BUG_067 | Closed | Khaled Wael | V2 | Edit_CF_04 | User is on the "Edit Custom Field" page. "Click on the ""Type"" dropdown. Expand the dropdown list. Verify all expected types are listed." | All types should be present in the dropdown. | All types are displayed correctly.
BUG_068 | Closed | Khaled Wael | V2 | Edit_CF_05 | User is on the "Edit Custom Field" page. "Click on the ""Type"" dropdown. Select a different type (e.g., ""Textarea""). Click ""Save"". Refresh the page." | The selected type should be saved. | The type is not saved; it reverts to the old value.
BUG_069 | Closed | Khaled Wael | V2 | Edit_CF_06 | User is on the "Edit Custom Field" page. "Do not select any type. Click ""Save"". Refresh the page." | The system should not allow saving without selection. | The type remains unchanged, but no error is shown.
BUG_070 | Closed | Khaled Wael | V2 | Edit_CF_07 | User is on the "Edit Custom Field" page. "Click on the ""Location"" dropdown. Expand the dropdown list. Verify all expected locations are listed." | All locations should be present in the dropdown. | All locations are displayed correctly.
BUG_071 | Closed | Khaled Wael | V2 | Edit_CF_08 | User is on the "Edit Custom Field" page. "Click on the ""Location"" dropdown. Select a different location (e.g., ""Address""). Click ""Save"". Refresh the page." | The selected location should be saved. | The location is not saved; it reverts to the old value.
BUG_072 | Closed | Khaled Wael | V2 | Edit_CF_09 | User is on the "Edit Custom Field" page. "Do not select any location. Click ""Save"". Refresh the page." | The system should not allow saving without selection. | The location remains unchanged, but no error is shown.
BUG_073 | Closed | Khaled Wael | V2 | Edit_CF_10 | User is on the "Edit Custom Field" page. "Click on the ""Sort Order"" field. Clear the existing value. Enter a valid number (e.g., ""2""). Click ""Save"". Refresh the page." | The new sort order should be saved and displayed after refresh. | The sort order is not saved; it reverts to the old value.
BUG_074 | Closed | Khaled Wael | V2 | Edit_CF_11 | User is on the "Edit Custom Field" page. "Click on the ""Sort Order"" field. Clear the existing value. Enter an invalid value (e.g., ""-5""). Click ""Save"". Refresh the page." | The system should show an error and prevent saving. | The sort order is not saved, but no error is displayed.
BUG_075 | Closed | Khaled Wael | V2 | Edit_CF_12 | User is on the "Edit Custom Field" page. "Click on the ""Sort Order"" field. Clear the existing value. Click ""Save"". Refresh the page." | The system should show an error and prevent saving. | The sort order is not saved, but no error is displayed.
BUG_076 | Closed | Khaled Wael | V2 | Edit_CF_14 | User is logged in as an admin and is on the Custom Fields page. "1. Click the ""Edit"" button beside an existing Custom Fields items. 2. Modify the required fields with valid data. 3. Click ""Save"" " | Submission updates successfully with a confirmation message | item can not be edited
BUG_077 | Closed | Khaled Wael | V2 | Edit_CF_15 | User is logged in as an admin and is on the Custom Fields page. "1. Click the ""Edit"" button beside an existing Custom Fields items. 2. Modify a field with invalid data (e.g., incorrect format). 3. Click ""Save"" button" | System displays an error message and does not save changes | item can not be edited
BUG_078 | Closed | Khaled Wael | V2 | Edit_CF_17 | User is logged in as an admin and is on the Custom Fields page. "1. Click the ""Edit"" button beside an existing Custom Fields items. 2. Do not modify any field. 3. Check if the ""Save"" or ""Update"" button is active." | "Save" button remains disabled | "Save" button remains enabled
BUG_079 | Closed | Khaled Wael | V2 | Edit_CF_18 | User is logged in as an admin and is on the Custom Fields page. "1. Click the ""Edit"" button beside an existing Custom Fields items. 2. Navigate back to the submissions list." | Updated data appears in the list | item can not be edited
BUG_080 | Closed | Khaled Wael | V2 | DEL_CF_03 | User is logged in as an admin and is on the Custom Fields page. "1. Open Custom Fields page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Custom Fields page." | All the selected items are removed from the UI after confirmation. | The selected items are not removed from the UI
BUG_081 | Closed | Khaled Wael | V2 | DEL_CF_04 | User is logged in as an admin and is on the Custom Fields page. "1. Open Custom Fields page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system." | Items is permanently removed from the database and do not reappear after refresh | Items are not removed from the database
BUG_082 | Closed | Khaled Wael | V2 | DEL_CF_08 | User is logged in as an admin and is on the Custom Fields page. "1. Open Custom Fields page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response." | A "Deletion successful" message appears after removing items. | The item is not deleted
BUG_083 | Closed | Khaled Wael | V2 | ADD_MAN_10 | User is logged in as an admin and is on the Manufacturers page. "1- Click on the plus icon on the top of the Manufacturers page 2- Leave the Manufacturers blank 3- submit the form" | The system do not show an error beside showing errors related to the other unfilled fields (not related to this case) | The system show an error indicating that this field is required beside showing errors related to the other unfilled fields (not related to this case)
BUG_084 | Closed | Khaled Wael | V2 | ADD_MAN_11 | User is logged in as an admin and is on the Manufacturers page. "1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Enter valid data in optional fields 4. Submit the form" | The item is added successfully, and a confirmation message should appear | The item is not added successfully, and a confirmation message should appear
BUG_085 | Closed | Khaled Wael | V2 | ADD_MAN_13 | User is logged in as an admin and is on the Manufacturers page. "1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Leave optional fields empty 4. Submit the form" | The item is added successfully | The item is not added successfully, and a confirmation message should appear
BUG_086 | Closed | Khaled Wael | V2 | ADD_MAN_15 | User is logged in as an admin and is on the Manufacturers page. "1. Click the Plus button on the top of the page 2. Enter the same data as an existing item 3. Submit the form" | The system display an error and prevent duplication | The item is not added successfully, and a confirmation message should appear
BUG_087 | Closed | Khaled Wael | V2 | ADD_MAN_18 | User is logged in as an admin and is on the Manufacturers page. "1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form" | A success message appear, confirming the addition | The item is not added successfully, and a confirmation message should appear
BUG_088 | Closed | Khaled Wael | V2 | ADD_MAN_19 | User is logged in as an admin and is on the Manufacturers page. "1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form" | The form reset to empty fields after submission | The item is not added successfully, and a confirmation message should appear
BUG_089 | Closed | Khaled Wael | V2 | ADD_MAN_20 | User is logged in as an admin and is on the Manufacturers page. "1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form" | The user is redirected to the item list page | The item is not added successfully, and a confirmation message should appear
BUG_090 | Closed | Khaled Wael | V2 | EDIT_MAN_10 | User is logged in as an admin and is on the Manufacturers page. "1- Click on the edit icon 2- Leave the Manufacturers blank 3- submit the form" | The system do not show an error | The system show an error indicating that this field is required
BUG_091 | Closed | Khaled Wael | V2 | EDIT_MAN_12 | User is logged in as an admin and is on the [PAGEHOLDER] page. "1. Click the ""Edit"" button beside an existing [PAGEHOLDER] items. 2. Modify the required fields with valid data. 3. Click ""Save"" " | Submission updates successfully with a confirmation message | item can not be edited
BUG_092 | Closed | Khaled Wael | V2 | EDIT_MAN_13 | User is logged in as an admin and is on the [PAGEHOLDER] page. "1. Click the ""Edit"" button beside an existing [PAGEHOLDER] items. 2. Modify a field with invalid data (e.g., incorrect format). 3. Click ""Save"" button" | System displays an error message and does not save changes | item can not be edited
BUG_093 | Closed | Khaled Wael | V2 | EDIT_MAN_15 | User is logged in as an admin and is on the [PAGEHOLDER] page. "1. Click the ""Edit"" button beside an existing [PAGEHOLDER] items. 2. Do not modify any field. 3. Check if the ""Save"" or ""Update"" button is active." | "Save" button remains disabled | "Save" button remains enabled
BUG_094 | Closed | Khaled Wael | V2 | EDIT_MAN_16 | User is logged in as an admin and is on the [PAGEHOLDER] page. "1. Click the ""Edit"" button beside an existing [PAGEHOLDER] items. 2. Navigate back to the submissions list." | Updated data appears in the list | item can not be edited
BUG_095 | Closed | Khaled Wael | V2 | DEL_MAN_03 | User is logged in as an admin and is on the Manufacturers page. "1. Open Manufacturers page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Manufacturers page." | All the selected items are removed from the UI after confirmation. | The selected items are not removed from the UI
BUG_096 | Closed | Khaled Wael | V2 | DEL_MAN_04 | User is logged in as an admin and is on the Manufacturers page. "1. Open Manufacturers page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system." | Items is permanently removed from the database and do not reappear after refresh | Items are not removed from the database
BUG_097 | Closed | Khaled Wael | V2 | DEL_MAN_08 | User is logged in as an admin and is on the Manufacturers page. "1. Open Manufacturers page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response." | A "Deletion successful" message appears after removing items. | The item is not deleted
BUG_098 | Closed | Khaled Wael | V2 | ADD_INFO_06 | User is logged in, text editor is accessible "1. Click on Bold, Underline, and other formatting options. 2. Change font style and size. 3. Change font color. 4. Add bullet and numbered lists. 5. Align text (left, center, right). 6. Insert table, image, and link. 7. Enable full-screen mode." | All editing options should apply changes correctly | All editing options does not apply changes correctly
BUG_099 | Closed | Khaled Wael | V2 | ADD_INFO_18 | User is logged in as an admin and is on the Information page. "1- Click on the add icon on the top of the Information page 2- Enter a invalid Sort Order in the Sort Order field 3- submit the form" | The System will not accept the Sort Order and will show an error indicating invalid entered Sort Order beside showing errors related to other unfilled fields not related to this test case | The System accepts the Sort Order and does not show an error indicating invalid entered Sort Order beside showing errors related to other unfilled fields not related to this test case
BUG_100 | Closed | Khaled Wael | V2 | ADD_INFO_30 | User is logged in as an admin and is on the Information page. "1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Enter valid data in optional fields 4. Submit the form" | The item is added successfully, and a confirmation message should appear | The item is not added successfully, and a confirmation message should appear
BUG_101 | Closed | Khaled Wael | V2 | ADD_INFO_32 | User is logged in as an admin and is on the Information page. "1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Leave optional fields empty 4. Submit the form" | The item is added successfully | The item is not added successfully, and a confirmation message should appear
BUG_102 | Closed | Khaled Wael | V2 | ADD_INFO_34 | User is logged in as an admin and is on the Information page. "1. Click the Plus button on the top of the page 2. Enter the same data as an existing item 3. Submit the form" | The system display an error and prevent duplication | The item is not added successfully, and a confirmation message should appear
BUG_103 | Closed | Khaled Wael | V2 | ADD_INFO_37 | User is logged in as an admin and is on the Information page. "1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form" | A success message appear, confirming the addition | The item is not added successfully, and a confirmation message should appear
BUG_104 | Closed | Khaled Wael | V2 | ADD_INFO_38 | User is logged in as an admin and is on the Information page. "1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form" | The form reset to empty fields after submission | The item is not added successfully, and a confirmation message should appear
BUG_105 | Closed | Khaled Wael | V2 | ADD_INFO_39 | User is logged in as an admin and is on the Information page. "1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form" | The user is redirected to the item list page | The item is not added successfully, and a confirmation message should appear
BUG_106 | Closed | Khaled Wael | V2 | DEL_INFO_03 | User is logged in as an admin and is on the Information page. "1. Open Information page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Information page." | All the selected items are removed from the UI after confirmation. | The selected items are not removed from the UI
BUG_107 | Closed | Khaled Wael | V2 | DEL_INFO_04 | User is logged in as an admin and is on the Information page. "1. Open Information page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system." | Items is permanently removed from the database and do not reappear after refresh | Items are not removed from the database
BUG_108 | Closed | Khaled Wael | V2 | DEL_INFO_08 | User is logged in as an admin and is on the Information page. "1. Open Information page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response." | A "Deletion successful" message appears after removing items. | The item is not deleted
BUG_109 | Closed | Khaled Wael | V2 | ADD_ORD_03 | 1- Click on the plus icon on the top of the Orders page 2- Leave the Store field blank 3- submit the form | The system do not show an error beside showing errors related to the other unfilled fields (not related to this case) | system show an error indicating required field
BUG_110 | Closed | Khaled Wael | V2 | ADD_ORD_08 | 1- Click on the plus icon on the top of the Orders page 2- Leave the Currency blank 3- submit the form | The system do not show an error beside showing errors related to the other unfilled fields (not related to this case) | system show an error indicating required field
BUG_111 | Closed | Khaled Wael | V2 | ADD_ORD_10 | 1- Click on the add icon on the top of the Orders page 2- Enter a invalid Customer 3- submit the form | The System will not accept the Customer and will show an error indicating invalid entered Customer beside showing errors related to other unfilled fields not related to this test case | The System accepts the Customer and do not show an error indicating invalid entered Customer beside showing errors related to other unfilled fields not related to this test case
BUG_112 | Closed | Khaled Wael | V2 | ADD_ORD_11 | 1- Click on the plus icon on the top of the Orders page 2- Leave the Customer field blank 3- submit the form | The system do not show an error beside showing errors related to the other unfilled fields (not related to this case) | system show an error indicating required field
BUG_113 | Closed | Khaled Wael | V2 | ADD_ORD_14 | 1- Click on the add icon on the top of the Orders page 2- Enter a invalid IC number in the IC number field 3- submit the form | The System will not accept the IC number and will show an error indicating invalid entered IC number beside showing errors related to other unfilled fields not related to this test case | The System accepts the IC number and do NOT show an error indicating invalid entered IC number beside showing errors related to other unfilled fields not related to this test case
BUG_114 | Closed | Khaled Wael | V2 | ADD_ORD_19 | 1- Click on the plus icon on the top of the Orders page 2- Leave the company name blank 3- submit the form | The system do not show an error beside showing errors related to the other unfilled fields (not related to this case) | system show an error indicating required field
BUG_115 | Closed | Khaled Wael | V2 | ADD_ORD_26 | 1- Click on the add icon on the top of the Orders page 2- Enter a invalid VAT number in the VAT number field 3- submit the form | The System does not accept the VAT number and shows an error indicating invalid entered VAT number beside showing errors related to other unfilled fields not related to this test case | The System accept the VAT number and does not shows an error indicating invalid entered VAT number beside showing errors related to other unfilled fields not related to this test case
BUG_116 | Closed | Khaled Wael | V2 | ADD_ORD_37 | 1- Click on the add icon on the top of the Orders page 2- Enter a invalid SECOND NAME 3- submit the form | The System will not accept the SECOND NAME and will show an error indicating invalid entered SECOND NAME beside showing errors related to other unfilled fields not related to this test case | The System accept the SECOND NAME and DOES NOT shows an error indicating invalid entered SECOND NAME beside showing errors related to other unfilled fields not related to this test case
BUG_117 | Closed | Khaled Wael | V2 | ADD_ORD_38 | 1- Click on the plus icon on the top of the Orders page 2- Leave the Second Name blank 3- submit the form | The system show an error indicating that this field is required beside showing errors related to the other unfilled fields (not related to this case) | system accepts it and do no show an error
BUG_118 | Closed | Khaled Wael | V2 | ADD_ORD_41 | 1- Click on the add icon on the top of the Orders page 2- Enter spaces in email 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_119 | Closed | Khaled Wael | V2 | ADD_ORD_42 | 1- Click on the add icon on the top of the Orders page 2- Start email with dot character 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_120 | Closed | Khaled Wael | V2 | ADD_ORD_43 | 1- Click on the add icon on the top of the Orders page 2- End email with dot character 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_121 | Closed | Khaled Wael | V2 | ADD_ORD_44 | 1- Click on the add icon on the top of the Orders page 2- Enter consecutive dot in email 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_122 | Closed | Khaled Wael | V2 | ADD_ORD_48 | 1- Click on the add icon on the top of the Orders page 2- Enter email without domain name 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_123 | Closed | Khaled Wael | V2 | ADD_ORD_49 | 1- Click on the add icon on the top of the Orders page 2- Enter dot character at end of username 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_124 | Closed | Khaled Wael | V2 | ADD_ORD_52 | 1- Click on the plus icon on the top of the Orders page 2- Enter an invalid Telephone number forms in the Telephone number field 3- submit the form | The System does not accept the telephone number and show an error indicating an invalid telephone number to it beside showing errors related to other unfilled fields not related to this test case | The System accept the telephone number and does not show an error indicating an invalid telephone number to it beside showing errors related to other unfilled fields not related to this test case
BUG_125 | Closed | Khaled Wael | V2 | ADD_ORD_54 | 1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Enter valid data in optional fields 4. Submit the form | The item should be added successfully, and a confirmation message should appear | The item is not added successfully, and a confirmation message should appear
BUG_126 | Closed | Khaled Wael | V2 | ADD_ORD_56 | 1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Leave optional fields empty 4. Submit the form | The item should be added successfully | The item is not added successfully, and a confirmation message should appear
BUG_127 | Closed | Khaled Wael | V2 | ADD_ORD_61 | 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | A success message should appear, confirming the addition | The item is not added successfully, and a confirmation message should appear
BUG_128 | Closed | Khaled Wael | V2 | ADD_ORD_58 | 1. Click the Plus button on the top of the page 2. Enter the same data as an existing item 3. Submit the form | The system should display an error and prevent duplication | The item is not added successfully, and a confirmation message should appear
BUG_129 | Closed | Khaled Wael | V2 | ADD_ORD_62 | 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | The form should reset to empty fields after submission | The item is not added successfully, and a confirmation message should appear
BUG_130 | Closed | Khaled Wael | V2 | ADD_ORD_63 | 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | The user should be redirected to the item list page | The item is not added successfully, and a confirmation message should appear
BUG_131 | Closed | Khaled Wael | V2 | ADD_ORD_65 | 1. Click the Plus button on the top of the page 2. observe all the items | All Orders related items are correctly displayed on the page | some Orders related items are not correctly displayed on the page
BUG_132 | Closed | Khaled Wael | V2 | DEL_OR_03 | 1. Open Orders page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Orders page. | All the selected items are removed from the UI after confirmation. | The selected items are not removed from the UI
BUG_133 | Closed | Khaled Wael | V2 | DEL_OR_04 | 1. Open Orders page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system. | Items is permanently removed from the database and do not reappear after refresh | Items are not removed from the database
BUG_134 | Closed | Khaled Wael | V2 | DEL_OR_08 | 1. Open Orders page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response. | A "Deletion successful" message appears after removing items. | The item is not deleted
BUG_135 | Closed | Khaled Wael | V2 | FILTER_REORD_09 | 1- Click on the filter icon on the top of the page 2- Enter an invalid "Total" 3- Click the "Filter" button | The system show an error indicating an entered invalid "Total" and does not allow filtering | The system does not show an error indicating an entered invalid "Total" and allow filtering
BUG_136 | Closed | Khaled Wael | V2 | EDIT_RE_ORD_09 | 1- Click on the Edit icon 2- Enter an invalid "Total" 3- submit the form | The system show an error indicating an entered invalid "Total" | The system does not show an error indicating an entered invalid "Total"
BUG_137 | Closed | Khaled Wael | V2 | EDIT_RE_ORD_11 | 1. Click the "Edit" button beside an existing Recurring Orders items. 2. Modify the required fields with valid data. 3. Click "Save" | Submission updates successfully with a confirmation message | item can not be edited
BUG_138 | Closed | Khaled Wael | V2 | EDIT_RE_ORD_12 | 1. Click the "Edit" button beside an existing Recurring Orders items. 2. Modify a field with invalid data (e.g., incorrect format). 3. Click "Save" button | System displays an error message and does not save changes | item can not be edited
BUG_139 | Closed | Khaled Wael | V2 | EDIT_RE_ORD_14 | 1. Click the "Edit" button beside an existing Recurring Orders items. 2. Do not modify any field. 3. Check if the "Save" or "Update" button is active. | "Save" button remains disabled | "Save" button remains enabled
BUG_140 | Closed | Khaled Wael | V2 | EDIT_RE_ORD_15 | 1. Click the "Edit" button beside an existing Recurring Orders items. 2. Navigate back to the submissions list. | Updated data appears in the list | item can not be edited
BUG_141 | Closed | Khaled Wael | V2 | FILTER_RE_ORD_13 | 1- Click on the filter icon on the top of the page 2- Enter a invalid date in the "Date Added" field 3- Click the "Filter" button | The system shows an error indicating an entered invalid date and does not allow filtering | The system does not show an error indicating an entered invalid date and allows filtering
BUG_142 | Closed | Khaled Wael | V2 | FILTER_RE_ORD_11 | 1- Click on the filter icon on the top of the page 2- Enter an invalid "Total" 3- Click the "Filter" button | The system show an error indicating an entered invalid "Total" and does not allow filtering | The system does not show an error indicating an entered invalid "Total" and allow filtering
BUG_143 | Closed | Khaled Wael | V2 | DEL_REORD_03 | 1. Open Recurring Orders page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Recurring Orders page. | All the selected items are removed from the UI after confirmation. | The selected items are not removed from the UI
BUG_144 | Closed | Khaled Wael | V2 | DEL_REORD_04 | 1. Open Recurring Orders page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system. | Items is permanently removed from the database and do not reappear after refresh | Items are not removed from the database
BUG_145 | Closed | Khaled Wael | V2 | DEL_REORD_08 | 1. Open Recurring Orders page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response. | A "Deletion successful" message appears after removing items. | The item is not deleted
BUG_146 | Closed | Khaled Wael | V2 | ADD_RE_06 | 1- Click on the add icon on the top of the page 2- Enter a invalid date in the "Order date" field 3- submit the form | The system shows an error indicating an entered invalid date | The system accepts it and does not show an error indicating an entered invalid
BUG_147 | Closed | Khaled Wael | V2 | ADD_RE_09 | 1- Click on the add icon on the top of the Returns page 2- Enter a invalid Customer 3- submit the form | The System will not accept the Customer and will show an error indicating invalid entered Customer beside showing errors related to other unfilled fields not related to this test case | The System accepts the Customer and do not show an error indicating invalid entered Customer beside showing errors related to other unfilled fields not related to this test case
BUG_148 | Closed | Khaled Wael | V2 | ADD_RE_10 | 1- Click on the plus icon on the top of the Returns page 2- Leave the Customer field blank 3- submit the form | The system do not show an error beside showing errors related to the other unfilled fields (not related to this case) | system show an error indicating required field
BUG_149 | Closed | Khaled Wael | V2 | ADD_RE_15 | 1- Click on the add icon on the top of the Returns page 2- Enter a invalid SECOND NAME 3- submit the form | The System will not accept the SECOND NAME and will show an error indicating invalid entered SECOND NAME beside showing errors related to other unfilled fields not related to this test case | The System accept the SECOND NAME and DOES NOT shows an error indicating invalid entered SECOND NAME beside showing errors related to other unfilled fields not related to this test case
BUG_150 | Closed | Khaled Wael | V2 | ADD_RE_16 | 1- Click on the plus icon on the top of the Returns page 2- Leave the Second Name blank 3- submit the form | The system show an error indicating that this field is required beside showing errors related to the other unfilled fields (not related to this case) | system accepts it and do no show an error
BUG_151 | Closed | Khaled Wael | V2 | ADD_RE_19 | 1- Click on the add icon on the top of the Returns page 2- Enter spaces in email 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_152 | Closed | Khaled Wael | V2 | ADD_RE_20 | 1- Click on the add icon on the top of the Returns page 2- Start email with dot character 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_153 | Closed | Khaled Wael | V2 | ADD_RE_21 | 1- Click on the add icon on the top of the Returns page 2- End email with dot character 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_154 | Closed | Khaled Wael | V2 | ADD_RE_22 | 1- Click on the add icon on the top of the Returns page 2- Enter consecutive dot in email 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_155 | Closed | Khaled Wael | V2 | ADD_RE_26 | 1- Click on the add icon on the top of the Returns page 2- Enter email without domain name 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_156 | Closed | Khaled Wael | V2 | ADD_RE_27 | 1- Click on the add icon on the top of the Returns page 2- Enter dot character at end of username 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_157 | Closed | Khaled Wael | V2 | ADD_RE_30 | 1- Click on the plus icon on the top of the Returns page 2- Enter an invalid Telephone number forms in the Telephone number field 3- submit the form | The System does not accept the telephone number and show an error indicating an invalid telephone number to it beside showing errors related to other unfilled fields not related to this test case | The System accept the telephone number and does not show an error indicating an invalid telephone number to it beside showing errors related to other unfilled fields not related to this test case
BUG_158 | Closed | Khaled Wael | V2 | ADD_RE_33 | 1- Click on the add icon on the top of the Returns page 2- Enter a invalid Products 3- submit the form | The System does not accept the Products and shows an error indicating invalid entered Products beside showing errors related to other unfilled fields not related to this test case | system accepts the field
BUG_159 | Closed | Khaled Wael | V2 | ADD_RE_37 | 1- Click on the add icon on the top of the Returns page 2- Enter a invalid Model 3- submit the form | The System does not accept the Model and shows an error indicating invalid entered Model beside showing errors related to other unfilled fields not related to this test case | system accepts the field
BUG_160 | Closed | Khaled Wael | V2 | ADD_RE_64 | 1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Enter valid data in optional fields 4. Submit the form | The item is added successfully, and a confirmation message should appear | The item is not added successfully, and a confirmation message should appear
BUG_161 | Closed | Khaled Wael | V2 | ADD_RE_66 | 1. Click the Plus button on the top of the page 2. Enter valid data in required fields 3. Leave optional fields empty 4. Submit the form | The item is added successfully | The item is not added successfully, and a confirmation message should appear
BUG_162 | Closed | Khaled Wael | V2 | ADD_RE_68 | 1. Click the Plus button on the top of the page 2. Enter the same data as an existing item 3. Submit the form | The system display an error and prevent duplication | The item is not added successfully, and a confirmation message should appear
BUG_163 | Closed | Khaled Wael | V2 | ADD_RE_71 | 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | A success message appear, confirming the addition | The item is not added successfully, and a confirmation message should appear
BUG_164 | Closed | Khaled Wael | V2 | ADD_RE_72 | 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | The form reset to empty fields after submission | The item is not added successfully, and a confirmation message should appear
BUG_165 | Closed | Khaled Wael | V2 | ADD_RE_73 | 1. Click the Plus button on the top of the page 2. Enter valid data 3. Submit the form | The user is redirected to the item list page | The item is not added successfully, and a confirmation message should appear
BUG_166 | Closed | Khaled Wael | V2 | EDIT_RE_06 | 1- click on the edit icon in page 2- Enter a invalid date in the "Order date" field 3- submit the form | The system shows an error indicating an entered invalid date | The system accepts it and does not show an error indicating an entered invalid
BUG_167 | Closed | Khaled Wael | V2 | EDIT_RE_09 | 1- click on the edit icon in Returns page 2- Enter a invalid Customer 3- submit the form | The System will not accept the Customer and will show an error indicating invalid entered Customer beside showing errors related to other unfilled fields not related to this test case | The System accepts the Customer and do not show an error indicating invalid entered Customer beside showing errors related to other unfilled fields not related to this test case
BUG_168 | Closed | Khaled Wael | V2 | EDIT_RE_10 | 1- click on the edit icon in Returns page 2- Leave the Customer field blank 3- submit the form | The system do not show an error beside showing errors related to the other unfilled fields (not related to this case) | system show an error indicating required field
BUG_169 | Closed | Khaled Wael | V2 | EDIT_RE_15 | 1- click on the edit icon in Returns page 2- Enter a invalid SECOND NAME 3- submit the form | The System will not accept the SECOND NAME and will show an error indicating invalid entered SECOND NAME beside showing errors related to other unfilled fields not related to this test case | The System accept the SECOND NAME and DOES NOT shows an error indicating invalid entered SECOND NAME beside showing errors related to other unfilled fields not related to this test case
BUG_170 | Closed | Khaled Wael | V2 | EDIT_RE_16 | 1- click on the edit icon in Returns page 2- Leave the Second Name blank 3- submit the form | The system show an error indicating that this field is required beside showing errors related to the other unfilled fields (not related to this case) | system accepts it and do no show an error
BUG_171 | Closed | Khaled Wael | V2 | EDIT_RE_19 | 1- click on the edit icon in Returns page 2- Enter spaces in email 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_172 | Closed | Khaled Wael | V2 | EDIT_RE_20 | 1- click on the edit icon in Returns page 2- Start email with dot character 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_173 | Closed | Khaled Wael | V2 | EDIT_RE_21 | 1- click on the edit icon in Returns page 2- End email with dot character 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_174 | Closed | Khaled Wael | V2 | EDIT_RE_22 | 1- click on the edit icon in Returns page 2- Enter consecutive dot in email 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_175 | Closed | Khaled Wael | V2 | EDIT_RE_26 | 1- click on the edit icon in Returns page 2- Enter email without domain name 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_176 | Closed | Khaled Wael | V2 | EDIT_RE_27 | 1- click on the edit icon in Returns page 2- Enter dot character at end of username 3- submit the form | The System will not accept the email and will show an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case | The System accept the email and does not shows an errors to it indicating invalid email beside showing errors related to other unfilled fields not related to this test case
BUG_177 | Closed | Khaled Wael | V2 | EDIT_RE_30 | 1- click on the edit icon in Returns page 2- Enter an invalid Telephone number forms in the Telephone number field 3- submit the form | The System does not accept the telephone number and show an error indicating an invalid telephone number to it beside showing errors related to other unfilled fields not related to this test case | The System accept the telephone number and does not show an error indicating an invalid telephone number to it beside showing errors related to other unfilled fields not related to this test case
BUG_178 | Closed | Khaled Wael | V2 | EDIT_RE_33 | 1- click on the edit icon in Returns page 2- Enter a invalid Products 3- submit the form | The System does not accept the Products and shows an error indicating invalid entered Products beside showing errors related to other unfilled fields not related to this test case | system accepts the field
BUG_179 | Closed | Khaled Wael | V2 | EDIT_RE_37 | 1- click on the edit icon in Returns page 2- Enter a invalid Model 3- submit the form | The System does not accept the Model and shows an error indicating invalid entered Model beside showing errors related to other unfilled fields not related to this test case | system accepts the field
BUG_180 | Closed | Khaled Wael | V2 | EDIT_RE_65 | 1. Click the "Edit" button beside an existing Returns items. 2. Modify the required fields with valid data. 3. Click "Save" | Submission updates successfully with a confirmation message | item can not be edited
BUG_181 | Closed | Khaled Wael | V2 | EDIT_RE_66 | 1. Click the "Edit" button beside an existing Returns items. 2. Modify a field with invalid data (e.g., incorrect format). 3. Click "Save" button | System displays an error message and does not save changes | item can not be edited
BUG_182 | Closed | Khaled Wael | V2 | EDIT_RE_68 | 1. Click the "Edit" button beside an existing Returns items. 2. Do not modify any field. 3. Check if the "Save" or "Update" button is active. | "Save" button remains disabled | "Save" button remains enabled
BUG_183 | Closed | Khaled Wael | V2 | EDIT_RE_69 | 1. Click the "Edit" button beside an existing Returns items. 2. Navigate back to the submissions list. | Updated data appears in the list | item can not be edited
BUG_184 | Closed | Khaled Wael | V2 | DEL_RE_03 | 1. Open Returns page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion in the pop-up. 5. Observe the Returns page. | The selected items are not removed from the UI | All the selected items are removed from the UI after confirmation.
BUG_185 | Closed | Khaled Wael | V2 | DEL_RE_04 | 1. Open Returns page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Refresh the page. 6. Verify the items are no longer in the system. | Items are not removed from the database | Items is permanently removed from the database and do not reappear after refresh
BUG_186 | Closed | Khaled Wael | V2 | DEL_RE_08 | 1. Open Returns page. 2. Select one or more checkboxes. 3. Click the Delete icon. 4. Confirm deletion. 5. Observe the system’s response. | The item is not deleted | A "Deletion successful" message appears after removing items.
BUG_187 | Closed | Khaled Wael | V2 | FILTER_RE_ORD_13 | 1- Click on the filter icon on the top of the page 2- Enter a invalid date in the "Date Added" field 3- Click the "Filter" button | The system shows an error indicating an entered invalid date and does not allow filtering | The system does not show an error indicating an entered invalid date and allows filtering